## Sheet1
Bug ID | Bug Description | testcase ID | assign to | notes | status
Driver
1 | when the driver add new image by camera the new one changed to black | 29 | Andriod | vergin 4.4 | Waiting
2 | there is no any notification alert | 43 -->47 | back end |  | Done
| msg notif. Go to the home not the msg section |  | Andriod |  | Waiting
| request with patch methods not supported on android vergin 4.4 so .. we can not test : accept order + complete oredr +send message+ change password |  | Backend |  | Waiting
| problem with map picker (set new address on map ) |  | Andriod | vergin 4.4 | Waiting
| error message when the internet connection go down or in any connection problem with service "حدث خطأ ... حاول مره اخري " |  | Andriod |  | Done
| when the driver change his phone NO .. In activation form if he add wronge pass it will pass and the phone will be saved |  | Backend |  | Waiting
| UI issue : هل نغير ال image path ف اي فورم بيختار فيها صوره ؟ في حاله تغيرها هتكون بأي شكل ؟ ف الديزاين ؟ |  | Andriod backend |  | Waiting
| vaildtion on phone NO ? |  | Backend |  | Waiting
| مش بيوصل للمندوب نوتيفكاشن "طلب استرداد" |  | Backend |  | Waiting
| in msg notification : first msg in the chat appear in the tap msg not last msg last msg not updated |  | Backend |  | Waiting
| driver cannot receive a notification from admin type ad |  | Backend |  | Waiting
| order completed on client ver before driver complete order and didn't appear in driver completed orders |  | backend |  | Waiting
| add new parameter to accepted notifocations (cancel navigation in android ) |  | backend |  | Waiting
| in IU) market cannot change : Country and city so make it unclickable can change only : اسم المشترك و الفون والايميل والنوع والجنسيه وكلمه المرور ورقم الهويه الشخصيه او الاقامه وصوره الهويه الشخصيه و الصوره الشخصيه و صوره رخضه القياده |  | backend |  | Waiting
market
| Problem in add product : issue in add multible photos of the product .. The field still empty even after add photos when click on add product there's no product will be added |  | Andriod |  | Done
| request with patch methods not supported on android vergin 4.4 so .. we can not test : change order status + change pass + change store status |  | backend Andriod |  | Waiting
| edit profile : issue in edit type of the store |  | Andriod |  | Waiting
| issue in UI : status of the store not matched with the button in the design |  | Andriod |  | Waiting
| هل نغير ال image path ف اي فورم بيختار فيها صوره ؟ في حاله تغيرها هتكون بأي شكل ؟ ف الديزاين ؟ |  | Andriod backend |  | Waiting
| market cannot receive a notification from admin type ad |  | backend |  | Waiting
| order completed before driver complete it |  | backend |  | Waiting
| ال id اللي بيتبعت ف ال puch notification مش صح |  | backend |  | Waiting
| (in IU) market cannot change : Country ,city , and store category so make it unclickable can change only : store name , store owner name, phone , mail,contact phone , address ورقم السجل الضريبي و رقم التسجيل ف معروف و صوره السجل الضريبي |  | backend |  | Waiting
| market cannot change : ورقم السجل الضريبي و رقم التسجيل ف معروف و صوره السجل الضريبي |  | backend |  | Waiting
Client
| when the Client add new image by camera (in registration form /edit form ) the new one changed to black then but action (register / edit) it worked |  | Andriod |  | Done 4.4 camera only
| request with patch methods not supported on android vergin 4.4 so .. we can not test : cancel order + send msg + change pass |  | backend |  | Waiting 4.4
| UI issues : (in the bottom main bar ) if we in any one of them like (المفضله /سله الشراء ..) it highlighted but it doesn’t work in the top main bar |  | Andriod | if we pressed prof, notf, navbar icons will be inactive | Waiting
| in order page when we reduce the products to be 0 the price does't does't calculated to be 0 also |  | Andriod |  | Done
| when the client change his phone NO .. In activation form if he add wronge pass it will pass and the phone will be saved |  | backend |  | Waiting
| in registration form the arrangement of alret Error msg (when the cleint miss filling the feilds) is not sorted from top to down |  | Andriod | low level issue | Waiting
| problem with map picker (set new address on map ) |  | Andriod | vergin 4.4 | Waiting
| هل نغير ال image path ف اي فورم بيختار فيها صوره ؟ في حاله تغيرها هتكون بأي شكل ؟ ف الديزاين ؟ |  | Andriod |  | Waiting
| client cannot receive a notification from admin type ad |  | Backend |  | Waiting
| order completed before driver complete it |  | Backend |  | Waiting
| client cannot change : Country and city so make it unclickable (in IU) can change only : name , phone , mail,and gender |  | Backend |  | Waiting
admin
| عند ارسال طلب استرجاع الرصيد من الادمن للمندوب قام المندوب بدفع ديونه ووظهر طلب دفع الدين فالادمن وعند محاوله تاكيد التحويل .. يتم خصم الرصيد من المندوب وليس من الاداره |  | Backend |  | Waiting
Store Admin
| there's no password validation (6 digits allowed when logining ) |  | Backend |  | Waiting
| when clicing on "لوحه التحكم " admin page will be shown not market admin |  | Backend |  | Waiting
new 12/2/2019
| there's no notification alert in 4.4 (type 3&5&9&11) |  | android |  | Waiting
| no alert in the notifications (ads to driver+new msg to driver) |  | backend |  | Waiting
| problems in notifications b/w cleint and market wrong notifications sent to wrong vergins of app |  | backend |  | Done